## Test Scenarios
Test Scenarios for Thirsty Wine Project :
Project Name | Thirsty Wine
Client | Thirsty Wine
Created By | Pavan Kumar
Creation Date | 13-11-2024
Approval Date | 16-11-2024
Test Scenario ID | Test Scenario Description | Number of Test Cases
TS_001 | Validate the working of Register Account functionality | 9
TS_002 | Validate the working of Login/Forget Password functionality | 12
TS_003 | Validate the working of Logout functionality | 4
TS_004 | Validate the working of Home Page functionality | 23
TS_005 | Validate the working of Search functionality | 16
TS_006 | Validate the working of 'Add to Cart' functionality | 14
TS_007 | Validate the working of 'Wish List' functionality | 5
TS_008 | Validate the working of Checkout functionality | 21
TS_009 | Validate the working of Account/Order History functionality | 8
TS_010 | Validate the working of Category/Price functionality | 9
TS_011 | Validate the working of Catalog functionality | 7
TS_012 | Validate the working of Support/outCompany functionality | 9

## Registration
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_001 | Validate the working of Register Account functionality | TC_RG_001 | Verify that all required fields should be marked with asterisk(*) | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option | N/A | all required fields should be marked with asterisk(*) | all required fields are marked with asterisk(*) | Pass | N/A
|  | TC_RG_002 | Verify that user should not be able to login with blank Name, Email, Password, Role | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Tap on submit Button without entering Name, Email, Password, Role | N/A | It should be shows an error " Please fill out this field " | It shows an error " Please fill out this field " | Pass | N/A
|  | TC_RG_003 | Verify that entering Numbers in name field istead of characters | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Enter the Name | Name : "123456" | It shows an Error " It looks like you've entered a mobile number. Please enter your name." | The "Name" field accepts numeric values, and no error is shown when entered. | Fail | https://drive.google.com/file/d/1_CY0PJxtMI8x1zgRDuLAyMxeVORnjVbW/view?usp=sharing
|  | TC_RG_004 | Verify that user should not be able to register by entering invalid Email ID | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Enter the Credentials | Email : "123456@gmail.com" | It shows an Error " Enter valid email ID." | The system allows users to enter an invalid email address without showing an error. | Fail | https://drive.google.com/file/d/12Siqkmc1_kqBeF-YHaNXdL16-de0eevW/view?usp=sharing
|  | TC_RG_005 | Verify that user should not be able to resgister the account without entering the correct Password | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Enter the Credentials | Password : "123456" | It shows an Error "Please choose a more secure password. It should be longer than 6 characters, unique to you and difficult for others to guess." | It takes the invalid Password and register successfully | Fail | https://drive.google.com/file/d/12Siqkmc1_kqBeF-YHaNXdL16-de0eevW/view?usp=sharing
|  | TC_RG_006 | Verify user can sign up with valid details. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Enter the Credentials | Name : Pavan Kumar Oggu Email : pavankumaroggu31@gmail.com Password : thirstywine@123 Role : user | User is registered successfully | User is registered successfully | Pass | N/A
|  | TC_RG_007 | Verify error message for already registered email. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4.Enter the Credentials | Email : pavankumaroggu31@gmail.com | Error message: "Email is already registered." | The system allows registration with an already used email without showing any error. | Fail | https://drive.google.com/file/d/1JooMXCkjAyXPhB8nC2CYK5GZlhNds_p1/view?usp=sharing
|  | TC_RG_008 | Verifry that 'Thank you for registering' email is sent to the registered email address as a confirmation for registering the account | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/register 2. Click on 'My Account' Dropmenu 3. Select 'SignUp' option 4. Enter new Account Details into the Mandatory Fields Name, Email, Password, Role 5. Click on 'Register' button 6. Check the email address used for registering the account | N/A | Validate a confirmation email for registering the account is sent to the registered email address. | The user doesn't receive a confirmation email after registration. | Fail | N/A
|  | TC_RG_009 | User Registration with Email as Name | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | User should be able to use email as a valid username if no duplicates exist. | Name : pavankumaroggu31@gmail.com | User should be able to use email as a valid username if no duplicates exist. | The system automatically uses the Gmail ID as the username instead of the entered name. | Fail | https://drive.google.com/file/d/1_CY0PJxtMI8x1zgRDuLAyMxeVORnjVbW/view?usp=sharing

## LoginForget Password
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_002 | Validate the working of Login/Forget Password functionality | TC_LP_001 | Validate logging into the Application using valid credentials | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | Email Address - pavanoltraining@gmail.com Password - 12345 | 1.User should be navigated to Login page 2.User should get logged in and taken to the 'Account' page | 1.User Successsfully Loggedin 2.User taken to the account page successfully | Pass
|  | TC_LP_002 | Validate logging into the Application using invalid credentials (i.e. Invalid email address and Invalid Password) | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | Email Address - xyzabc123@gmail.com Password - xyzabc123 | 1. Warning message with the text 'Warning: No match for E-Mail Address and/or Password.' should be displayed | 1. User login failed but it doesnt show any error about no match for e-mail address and password | Fail | https://drive.google.com/file/d/1lf3m_ARJj5po-YCdGiOEi7myaz5iWTwU/view?usp=sharing
|  | TC_LP_003 | Validate logging into the Application using invalid email address and valid Password | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | Email Address - xyzabc123@gmail.com Password - 12345 | 1. Warning message with the text 'Warning: No match for E-Mail Address and/or Password.' should be displayed | 1. User login failed but it doesnt show any error about no match for e-mail address and password | Fail | https://drive.google.com/file/d/1lf3m_ARJj5po-YCdGiOEi7myaz5iWTwU/view?usp=sharing
|  | TC_LP_004 | Validate logging into the Application using valid email address and invalid Password | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | Email Address - pavanoltraining@gmail.com Password - xyzabc123 | 1. Warning message with the text 'Warning: No match for E-Mail Address and/or Password.' should be displayed | 1. User login failed but it doesnt show any error about no match for e-mail address and password | Fail | https://drive.google.com/file/d/1lf3m_ARJj5po-YCdGiOEi7myaz5iWTwU/view?usp=sharing
|  | TC_LP_005 | Validate logging into the Application without providing any credentials | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | N/A | 1. Warning message with the text 'Please fill out this field.' should be displayed | It shows please out this field | Pass
|  | TC_LP_006 | Validate 'Forgotten Password' link is available in the Login page and is working | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Select the forget password option | N/A | 1. User should be taken to 'Login' page and 'Forgotten Password' link should be displayed in the page | There is no "Forgot Password" link or option available on the login page. | Fail | https://drive.google.com/file/d/1g8hweCj-2fsXW1O9ffChl7CKPTtICcFq/view?usp=sharing
|  | TC_LP_007 | Verify that correct error message should be displayed when user entered Blank email and password | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | N/A | 1. Warning message with the text 'Please fill out this field.' should be displayed | It show the Please fill out this field. | Pass
|  | TC_LP_008 | Verify login page will appear after click on Login Page | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | N/A | Login Page screen will appear | As Expected | Pass
|  | TC_LP_009 | Login with Account Locked Due to Multiple Failed Attempts | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | N/A | System should display an error message: "Your account has been locked due to multiple failed login attempts." | It doesn't any error about multiple login attempts | Fail | https://drive.google.com/file/d/1lf3m_ARJj5po-YCdGiOEi7myaz5iWTwU/view?usp=sharing
|  | TC_LP_010 | Login with Social Media Login (e.g., Google) | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Enter the credentials 5. Click the login button | N/A | User should be logged in successfully via Google authentication and redirected to the homepage. | There is no social media option to login, user login with their registered credentials | Fail | https://drive.google.com/file/d/1g8hweCj-2fsXW1O9ffChl7CKPTtICcFq/view?usp=sharing
|  | TC_LP_011 | Check for "Forgot Password" Link on the Login Page | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Select the forget password option | N/A | There should be no "Forgot Password" link or option on the login page. | There is no "Forgot Password" link or option available on the login page. | Fail | https://drive.google.com/file/d/1g8hweCj-2fsXW1O9ffChl7CKPTtICcFq/view?usp=sharing
|  | TC_LP_012 | Verify User Account Recovery Alternative Methods | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the signup page 4. Select the forget password option | N/A | The website should provide alternative ways (like contacting customer support) to recover the account, since the "Forgot Password" option is missing. | There is no opions is there to recover the passwrod | Fail | https://drive.google.com/file/d/1g8hweCj-2fsXW1O9ffChl7CKPTtICcFq/view?usp=sharing

## Logout
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_003 | Validate the working of Logout functionality | TC_LT_001 | Logout with User Profile Redirected to Login Page | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the home page 4. Select the logout option | N/A | User should be redirected to the login page after logging out. | As Expected | Pass
|  | TC_LT_002 | Logout When Network Connection is Lost | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the home page 4. Select the logout option | N/A | System should either log the user out or show a network error message, but once the network is reconnected, the session should be terminated. | As Expected | Pass
|  | TC_LT_003 | Validate Logging out by selecting Logout option from 'Right Column' options | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the home page 4. Select the logout option | N/A | Logging out by selecting Logout option from 'Right Column' options | As Expected | Pass
|  | TC_LT_004 | Validate Logging out by selecting Logout option from 'My Account' dropmenu | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3. Go to the home page 4. Select the logout option | N/A | Logging out by selecting Logout option from 'Right Column' options | As Expected | Pass

## Home Page
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_004 | Validate the working of Home Page functionality | TC_HP_001 | Verify the home page is displayed after login or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | home page displayed after login | As expected | Pass
|  | TC_HP_002 | Verify the user name is displayed on home page or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | User name is present | As expected | Pass
|  | TC_HP_003 | Verify the featured product is available or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | featured product are available on home page | As expected | Pass
|  | TC_HP_004 | Verify the search functionality is present or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | search functionality is present | As expected | Pass
|  | TC_HP_005 | Verify the product displayed on homepage clickable or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4.Select the product |  | product should be clickable | As expected | Pass
|  | TC_HP_006 | Verify the user profile section is available on home page or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | Profile section should be available | Profile section isn't open | Fail | https://drive.google.com/file/d/1UaLR6QOXXdl3vhcHDJQX6i8MOBzLdDgf/view?usp=sharing
|  | TC_HP_007 | Verify the header section on home page is available or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | header section on home page is available | As expected | Pass
|  | TC_HP_008 | Verify the header section on home page is clickable or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | header section on home page is clickable | As expected | Pass
|  | TC_HP_009 | Verify the header section links on home page is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | header section links on home page is open | As expected | Pass
|  | TC_HP_010 | Verify that when user open the Red optoin in header section links on home page, it displays the data or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Red option |  | It displays the Red Wine | As expected | Pass
|  | TC_HP_011 | Verify that when user open the White optoin in header section links on home page, it displays the data or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the White option |  | It displays the White Wine | As expected | Pass
|  | TC_HP_012 | Verify that when user open the Rose optoin in header section links on home page, it displays the data or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Rose option |  | It displays the Rose Wine | As expected | Pass
|  | TC_HP_013 | Verify that when user open the Sparkling optoin in header section links on home page, it displays the data or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Sparkling option |  | It displays the Sparkling Wine | As expected | Pass
|  | TC_HP_014 | Verify that when user open the Promotions optoin in header section links on home page, it displays the data or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Promotions option |  | It displays the Promotions page | The "promotion page" section does not display any products and shows a blank page instead. | Fail | https://drive.google.com/file/d/1ssUSz-osVrm0mfZ6iFs-5vb21aiZClfJ/view?usp=sharing
|  | TC_HP_015 | Verify that when user open the Set&Gifts optoin in header section links on home page, it displays the data or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Set&Gifts option |  | It displays the Set&Gifts page | The "Set&Gifts" section does not display any products and shows a blank page instead. | Fail | https://drive.google.com/file/d/1ssUSz-osVrm0mfZ6iFs-5vb21aiZClfJ/view?usp=sharing
|  | TC_HP_016 | Verify that wine products in "What would you like?" are visible | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | Wine products should be visible in the "What would you like?" section on the homepage. | As expected | Pass
|  | TC_HP_017 | Verify that each wine product in "What would you like?" section is clickable | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | Each wine product should be clickable, and clicking it should redirect to the product detail page | As Expected | Pass
|  | TC_HP_018 | Verify that clicking the "What Would You Like?" option in the header displays data on the homepage. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page |  | After clicking the "What Would You Like?" option, the homepage should display the relevant data (e.g., wine products, categories, or any other relevant content) without any errors. | The "What would you like" section does not display any products and shows a blank page instead. | Fail | N/A
|  | TC_HP_019 | Verify that wine products in the "Best Seller" section are clickable and open correctly. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Best seller option and click the product |  | Wine products in the "Best Seller" section should be clickable and open the respective product details page or show more information about the product without any errors. | As expected | Pass
|  | TC_HP_020 | Verify that wine products in the "Great Deals" section are clickable and open correctly. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Great Deals option and click the product |  | Wine products in the "Great Deals" section should be clickable and open the respective product details page or display more product information correctly. | As expected | Pass
|  | TC_HP_021 | Verify that wine products in the "Highly Rated" section are clickable and open correctly. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Highly Rated option and click the product |  | Wine products in the "Highly Rated" section should be clickable and open the respective product details page or display more product information correctly. | As expected | Pass
|  | TC_HP_022 | Verify that Blog & News articles about wines are open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Blog & News option |  | Verify that Blog & News articles about wines are open | Blog & News page is not responding | Fail | https://drive.google.com/file/d/1i3HxjHFisJMJa9GijueZmpXU-BBQkLLf/view?usp=sharing
|  | TC_HP_023 | Verify that navigate to instagram page when user clicks the "We are on Instagram" options | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the we are on instagram option |  | user navigate to instagram page when user clicks the "We are on Instagram" options | instagramis not responding | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing

## Search
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_005 | Validate the working of Search functionality | TC_SH_001 | Validate searching with an existing Product Name | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Product Name : Amarone della Valpolicella | 1. Searched product should be displayed in the search results | As Expected | Pass | N/A
|  | TC_SH_002 | Validate searching with a non existing Product Name | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Product Name : One Plus | 1. 'There is no product that matches the search criteria' should be displayed in the Search Results page | It didn't display any error, it gives empty page | Fail | https://drive.google.com/file/d/13RbRX-evCpP5PYca2yHJtbsBEm58urp_/view?usp=sharing
|  | TC_SH_003 | Validate searching without providing any Product Name | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | N/A | 1.'There is no product that matches the search criteria' should be displayed in the Search Results page | There is no response from the search functionality,It didnt give any message | Fail | https://drive.google.com/file/d/10g0wC0dJm6HvpKR0NeFbpLwKCdtLCRR5/view?usp=sharing
|  | TC_SH_004 | Validate searching for a product after login to the Application | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Product Name : Amarone della Valpolicella | 1. Searched product should be displayed in the search results | As Expected | Pass | N/A
|  | TC_SH_005 | Validate the User can select how many produts can be displayed in the Search Results | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Product Name : Amarone della Valpolicella | 1. More than one product should be displayed in the search results page | As Expected | Pass | N/A
|  | TC_SH_006 | Search with a product name containing spaces | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Product Name : Riesling Trocken | The system should return results for "Pinot Noir", treating the space as a valid part of the search term. | As Expected | Pass | N/A
|  | TC_SH_007 | Validate the Search functionality in all the supported environments | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | N/A | 1. Search functionality should work correctly in all the supported environments | As Expected | Pass | N/A
|  | TC_SH_008 | Verify that user should be able to get the thirsty wine in search box or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | N/A | User should be able to click on the search page | As Expected | Pass | N/A
|  | TC_SH_009 | Verify that when user enters single letter in the search box then suggested product list should be displayed | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | N/A | suggested product list should be displayed when user enters single letter in the search box | As Expected | Pass | N/A
|  | TC_SH_010 | Verify that user is able to get search result when enters combination of alpha special characters | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | "Wine2024" | system should return search results related to "Wine2024", either a specific product or relevant content | As Expected | Pass | N/A
|  | TC_SH_011 | Verify that user is able to enters with Special Characters | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | @wine# | System should either return results that match the special characters in the search term or display a no results message | As Expected | Pass | N/A
|  | TC_SH_012 | Search with Alphanumeric and Special Characters Combined | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Wine@123# | System should return relevant results containing products or content related to "Wine@123#". | As Expected | Pass | N/A
|  | TC_SH_013 | Verify the Red wine in search functionality | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Product Name : Red Wine | It shows the red wine products | As Expected | Pass | N/A
|  | TC_SH_014 | Verify the White wine in search functionality | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | White wine | Search functionality shoud displays the white wine | Search functionality displays the all data istead of giving only White wine | Fail | https://drive.google.com/file/d/1tQjnQQoIBcowdyq0hW9ypJJ4jUYNW-d_/view?usp=sharing
|  | TC_SH_015 | Verify the Rose wine in search functionality | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Rose Wine | Search functionality shoud displays the Rose wine | It displays the red wine instead Rose wine | Fail | https://drive.google.com/file/d/1VntsjfrODd6Ye3J7nCm4ooaYORtAYEa_/view?usp=sharing
|  | TC_SH_016 | Verify the Wine sets in search functionality | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the search bar | Wine sets | Search functionality shoud displays the Wine sets | It displays the red wine instead of wine sets | Fail | https://drive.google.com/file/d/1FKpo7zsdn25ZW9Kce4Diu2cfx2PsOolG/view?usp=sharing

## Add to Cart
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_006 | Validate the working of 'Add to Cart' functionality | TC_AC_001 | Verify that the shopping cart icon is displayed as expected or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | shopping cart icon is displayed as expected | As expected | Pass
|  | TC_AC_002 | Verify that the shopping cart icon is clickable or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option | N/A | shopping cart icon is clickable | As expected | Pass
|  | TC_AC_003 | Verify that the user is able to add items into the cart or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user is able to add items into the cart | As expected | Pass
|  | TC_AC_004 | Verify if the user increase the number of items then the cart should be reflected as per qunatities | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user increase the number of items then the cart should be reflected as per qunatities | As expected | Pass
|  | TC_AC_005 | Verify if the user decreases the items the number of items then the cart should be reflected as per quantities | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user decreases the items the number of items then the cart should be reflected as per quantities | Decreasing item quantity in the cart does not update the cart correctly. | Fail | https://drive.google.com/file/d/16IW3xdlPcBOOVmyTIZqefbOQZ55ZBByD/view?usp=sharing
|  | TC_AC_006 | Verify that the user is able to click on the cart icon button when the cart is empty | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user is able to click on the cart icon button when the cart is empty | As expected | Pass
|  | TC_AC_007 | Verify that the user is click on the cart icon button then the user should navigate to the shopping cart page | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user is click on the cart icon button then the user should navigate to the shopping cart page | As expected | Pass
|  | TC_AC_008 | Verify that the user is able to remove the products from the cart | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user is able to remove the products from the cart | As expected | Pass
|  | TC_AC_009 | Verify that the user is able to increase the products from the cart | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user is able to increase the products from the cart | As expected | Pass
|  | TC_AC_010 | Verify that the user is able to decrease the products from the cart | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user is able to decrease the products from the cart | As expected | Pass
|  | TC_AC_011 | Verify that the total price should be corrected | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | total price should be corrected | As expected | Pass
|  | TC_AC_012 | Verify that checkout option should be working properly | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | proceed checkout option should be working properlyVerify if the user removes all items from the cart,the cart should be displayed as empty | As expected | Pass
|  | TC_AC_013 | Verify if the user removes all items from the cart,the cart should be displayed as empty | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user removes all items from the cart,the cart should be displayed as empty | As expected | Pass
|  | TC_AC_014 | Verify if the user place an order successfully then the cart should be empty | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the Add to Cart option 5. Go to the cart | N/A | user place an order successfully then the cart should be empty | As expected | Pass

## Wishlist
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_007 | Validate the working of 'Wish List' functionality | TC_WL_001 | Verify that a user can add a product to the wishlist. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | The product should be added to the Wishlist. | As expected | Pass | N/A
|  | TC_WL_002 | Verify that a user can view the wishlist. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-130 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | The Wishlist should display the added products correctly with details like product name, image, price, and quantity. | Wishlist is not displays the product | Fail | https://drive.google.com/file/d/1Wdsj9eedcDvyHOTK6jtDJ9jh3y63CP_A/view?usp=sharing
|  | TC_WL_003 | Verify that the "Add to Wishlist" button works correctly for products in the search results. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-131 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | "Add to Wishlist" button works correctly for products in the search results. | As expected | Pass | N/A
|  | TC_WL_004 | Verify that a user receives a confirmation message when adding a product to the wishlist. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-132 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | A confirmation message should appear indicating that the product has been successfully added to the wishlist. | As expected | Pass | N/A
|  | TC_WL_005 | Verify that the user can add products to the wishlist from the product listing page. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-133 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. select wishlist button | N/A | the product should be added to the wishlist, and the wishlist count should be updated. | The product is not added to the wishlist | Fail | https://drive.google.com/file/d/1Wdsj9eedcDvyHOTK6jtDJ9jh3y63CP_A/view?usp=sharing

## Checkout
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_008 | Validate the working of Checkout functionality | TS_CA_001 | Verify that the user can proceed to checkout from the cart. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart | N/A | The user should be redirected to the checkout page from the cart. | As Expected | Pass | N/A
|  | TS_CA_002 | Verify that the checkout page displays the correct product details. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart | N/A | The checkout page should display the correct product name, price, quantity, and total cost. | As Expected | Pass | N/A
|  | TS_CA_003 | Verify that enter the address in new customer option is taken or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option and enter the name,number, email | Name : Pavan, Phone Number : 9059007119 Gmail : pavankumaroggu31@gmail.com | enter the address in new customer option is taken | As Expected | Pass | N/A
|  | TS_CA_004 | Verify that User is able to enter the numbers in "NAme" field in the address form | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Name : 123, Phone Number : 9059007119 Gmail : pavankumaroggu31@gmail.com | It shows an error " enter the name" | User is able to enter numbers in the "Name" field in the address form. | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_005 | Verify that enter the invalid number in address | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Name : 123, Phone Number : 123 Gmail : pavankumaroggu31@gmail.com | It shows an error " enter the valid mobile number" | It accepts the invlalid mobile number | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_006 | Verify that enter the invalid email in address | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Name : 123, Phone Number : 123 Gmail : 123@gmail.com | It shows an error " enter the valid email" | It accepts the invlalid email | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_007 | Verify that i have an account option in checkout page open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | i have an account option in checkout page open | As Expected | Pass | N/A
|  | TS_CA_008 | Verify that it shows the saved address in checkout option or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | it shows the saved address in checkout option | It doent't show the saved address | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_009 | Verify that the user can enter and select a valid shipping address. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | The valid shipping address should be entered and displayed correctly on the checkout page. |  | Pass | N/A
|  | TS_CA_010 | Verify that the user can enter invalid shipping address. | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | It shows error"enter the valid address,mobile,email" | It accepts the invalid addres and proceed to checkout the payment | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_011 | Verify that enter the invalid current address | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | It shows error"enter the valid current address" | It accepts the invalid current addres and proceed to checkout the payment | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_012 | Verify that enter the numbers instead of giving characters in city name option | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | City : 123 | It shows error"enter the city name" | The "City" field accepts numeric values, which should only accept alphabetic characters. | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_013 | Verify that enter the numbers instead of giving characters in state name option | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | State : 123 | It shows error"enter the state name" | The "State" field accepts numeric values, which should only accept alphabetic characters. | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_014 | Verify that enter the numbers instead of giving characters in district name option | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Dstrict : 123 | It shows error"enter the district name" | The "District" field accepts numeric values, which should only accept alphabetic characters. | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_015 | Verify that enter the invalid pincode | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | Pincode : 123 | It shows error"enter the valid pincode" | The "Pincode" field accepts invalid pincode | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing
|  | TS_CA_016 | Verify that online payment method is selecting or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | online payment method is selecting | As Expected | Pass | N/A
|  | TS_CA_017 | Verify that online payment upon receipt method is selecting or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | online payment upon receipt method is selecting | As Expected | Pass | N/A
|  | TS_CA_018 | verify that continue the payment button work or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | continue the payment button is work | As Expected | Pass | N/A
|  | TS_CA_019 | Verify that payment is successfull or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | payment is successfull | As Expected | Pass | N/A
|  | TS_CA_020 | verify that user receives the thankyou for your purchage message or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | user receives the thankyou for your purchage message | As Expected | Pass | N/A
|  | TS_CA_021 | verify that user receives the emaiol confirmation message or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. Select the product 5. Add to the cart 6. Go to the Cart 7. Go to the checkout option | N/A | user receives the emaiol confirmation message | User didn't receive any email after completing the checkout process | Fail | https://drive.google.com/file/d/1BIwfAF6LfZR5GRtyml89Sw_WczYmFEpG/view?usp=sharing

## AccountOrderHistory
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_009 | Validate the working of Account/Order History functionality | TC_AO_001 | Verify that my account option is there or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account | N/A | my account option is there | As expected | Pass | N/A
|  | TC_AO_002 | Verify that my account option is clickable or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account | N/A | my account option is clickable | It is not clickable | Fail | https://drive.google.com/file/d/1uXWcVHB_whilzLmyVP4tEQBfmSZJ8ZPS/view?usp=sharing
|  | TC_AO_003 | Verify that my account option is responding/open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account | N/A | my account option is responding/open | It is not responding/open | Fail | https://drive.google.com/file/d/1uXWcVHB_whilzLmyVP4tEQBfmSZJ8ZPS/view?usp=sharing
|  | TC_AO_004 | Verify that my orders option is there or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Orders option is there in my account drop down list | N/A | my orders option is there | There is no my orders option is there | Fail | https://drive.google.com/file/d/1uXWcVHB_whilzLmyVP4tEQBfmSZJ8ZPS/view?usp=sharing
|  | TC_AO_005 | Verify that order information option is there or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Orders information is there in my account drop down list | N/A | order information option is there | There is no order information option is there | Fail | https://drive.google.com/file/d/1uXWcVHB_whilzLmyVP4tEQBfmSZJ8ZPS/view?usp=sharing
|  | TC_AO_006 | Verify that product returns option is there or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Product Returns is there in my account drop down list | N/A | product returns option is there | There is no product returns option is there | Fail | https://drive.google.com/file/d/1uXWcVHB_whilzLmyVP4tEQBfmSZJ8ZPS/view?usp=sharing
|  | TC_AO_007 | Verify that your transactions option is there or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Your Transactions is there in my account drop down list | N/A | your transactions option is there | There is no your transaction option is there | Fail | https://drive.google.com/file/d/1uXWcVHB_whilzLmyVP4tEQBfmSZJ8ZPS/view?usp=sharing
|  | TC_AO_008 | Verify that order history option is there or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page 4. In Home Page Right side there is a option called My Account 5. my Order history is there in my account drop down list | N/A | order history option is there | There is no order history option is there | Fail | https://drive.google.com/file/d/1uXWcVHB_whilzLmyVP4tEQBfmSZJ8ZPS/view?usp=sharing

## CategoryPrice
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_010 | Validate the working of Category/Price functionality | TC_CP_001 | Verify that selecting the All option in category is working or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select All product option in category | N/A | selecting the All option in category is working | As Expected | Pass | N/A
|  | TC_CP_002 | Verify that All products is displayed or not in All option | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select All product option in category | N/A | All products is displayed | As Expected | Pass | N/A
|  | TC_CP_003 | Verify that selecting the White wine in category | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select White wine product option in category | N/A | It shows only white wine products | Category option shows sprankling products | Fail | https://drive.google.com/file/d/1gLqI16MVTnUUKPvPsZ0XZxv7tSCVgAnQ/view?usp=sharing
|  | TC_CP_004 | Verify that selecting the Red wine in category | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select Red wine wine product option in category | N/A | It shows only Red wine products | As Expected | Pass | N/A
|  | TC_CP_005 | Verify that selecting the Rose wine in category | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select Rose wine wine product option in category | N/A | It shows only Rose wine products | Category Option shows sprankling products | Fail | https://drive.google.com/file/d/1EtMVHACUhZLx6z77KuONOc_NviDpYSJX/view?usp=sharing
|  | TC_CP_006 | Verify that selecting the price between the 0$-50$ | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select price range option in Price | N/A | It shows only 0$-50$ products | As Expected | Pass | N/A
|  | TC_CP_007 | Verify that selecting the price between the 50$-100$ | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select price range option in Price | N/A | It shows only 50$-100$ products | As Expected | Pass | N/A
|  | TC_CP_008 | Verify that selecting the price between the 100$-150$ | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select price range option in Price | N/A | It shows only 100$-150% products | As Expected | Pass | N/A
|  | TC_CP_009 | Verify that selecting the price between the 150$ above | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Click on the one option in header section 3. Select price range option in Price | N/A | It shows only 150% Above products | As Expected | Pass | N/A

## Catalog
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_011 | Validate the working of Catalog functionality | TC_CA_001 | Verify that all products shown in catalog option or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | all products shown in catalog option | As expected | Pass | N/A
|  | TC_CA_002 | Verify that Red wine product is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Red wine product is open | Red wine product does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_CA_003 | Verify that Rose wine product is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Rose wine product is open | Rose wine product does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_CA_004 | Verify that White wine product is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | White wine product is open | White wine product does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_CA_005 | Verify that Sparkling wine product is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Sparkling wine product is open | Sparkling wine product does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_CA_006 | Verify that Promotion page is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | promotion page is open | Promotion page does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_CA_007 | Verify that set & Gifts page is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Set &Gifts page is open | Set & Gifts page does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing

## SupportOur Company
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Pre-requisite | Pre-Conditions | Version | Test-Steps | Test Data | Expected Result | Actual Result | Status | ScreenShot/Video
TS_012 | Validate the working of Support/outCompany functionality | TC_SU_001 | Verify that all products shown in supprt option or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | all products shown in catalog option | As expected | Pass | N/A
|  | TC_SU_002 | Verify that FAQ page is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | FAQ page is open | FAQ Page does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_SU_003 | Verify that Terms of Use is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Terms Of Use Option is open | Terms Of Use Option does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_SU_004 | Verify that Privacy Policy is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Privacy Ploicy is open | Privacy Policy Option does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_SU_005 | Verify that Delivery and Payment page is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Delivery and Payment page is open | Delivery and payment page does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_SU_006 | Verify that Returns and Exchange is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Returns and Exchange is open | Returns and Exchange Option does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_SU_007 | Verify that AboutUs page is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | About Us page is open | About Us Option does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_SU_008 | Verify that Contact Us page is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Contact Us page is open | Contact Us Option does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing
|  | TC_SU_009 | Verify that Reviews page is open or not | https://pay-pal-pioneers-068.vercel.app/register | 1.Good internet 2.Laptop 3.URL 4.Browser 5.User on the login page | Chrome-129 | 1. Open the Application URL : https://pay-pal-pioneers-068.vercel.app/ 2. Login to the account 3.Go to the home page | N/A | Reviews page is open | Review Page does not open when clicked. | Fail | https://drive.google.com/file/d/12KI1DekY-vjH8_UcMWj4mLGLMsGFHtFq/view?usp=sharing